## Slide 1: INTELLIGENT REMOTE HEALTHCARE AND ASSISTED LIVING ECOSYSTEM
KNOWLEDGE INSTITUTE OF TECHNOLOGY

## Slide 2
OBJECTIVE
Continuously monitor elderly and chronically ill patients remotely.
Monitor heart rate, SpO₂, temperature and physical activity.
Detect abnormal health conditions and fall events automatically.
SOLUTION
Wearable sensors collect patient health data.
IoT gateway transfers data to the cloud.
AI analyses vital signs and detects anomalies and falls.
Caregiver and doctor dashboards provide real-time monitoring.
IMPACT
Enables continuous out-of-hospital healthcare monitoring.
Provides rapid emergency alerts.
Supports medication adherence and health-trend monitoring.
Reduces the risk of undetected medical emergencies.
KNOWLEDGE INSTITUTE OF TECHNOLOGY

## Slide 3: Engineering Design Process
REQUIREMENT & PLANNING
Identified the need for continuous remote monitoring.
Defined requirements for sensing, alerts and assisted living.
DEVELOPMENT
Developed wearable sensing and IoT communication modules.
Implemented AI anomaly detection and fall detection.
INTEGRATION
Connected sensors, gateway, cloud, AI, notifications and dashboards.
TESTING & VALIDATION
Performed functional, module-level and integration testing.
Verified monitoring, alerts, medication and reporting functions.
KNOWLEDGE INSTITUTE OF TECHNOLOGY

## Slide 4: Process Table
KNOWLEDGE INSTITUTE OF TECHNOLOGY
PHASE | ENGINEERING STEPS | KEY ACTIVITIES & OUTCOME
Definition | Requirement Analysis | Identified remote healthcare requirements.
Development | System Design & Development | Developed sensing, AI and application modules
Integration | System Integration | Connected wearable, gateway, cloud and dashboards
Realization | Testing & Validation | Verified complete system functionality

## Slide 5: List of Activities
KNOWLEDGE INSTITUTE OF TECHNOLOGY
Literature Survey Studied IoT health monitoring, wearable sensors, AI analytics and fall detection.
Requirement Analysis Identified requirements for continuous sensing, alerts and remote monitoring.
Technology Selection Selected ESP32, BLE, Wi-Fi/MQTT, React, Node.js, Firebase and AI services.
System Development Developed sensor, gateway, backend, AI and dashboard modules.
System Integration Integrated authentication, cloud database, alerts, medication and reporting.
Testing & Validation Performed functional, module and end-to-end integration testing.

## Slide 6: Activity Duration Table
ID | Activity Description | Duration (Hours)
A | Requirement Analysis | 30
B | Literature Survey | 25
C | System & UI Design | 40
D | Software Development | 55
E | AI / IoT Integration | 30
F | Testing & Optimization | 40
G | Documentation & Presentation | 30
Total | Project Duration | 250 Hours
KNOWLEDGE INSTITUTE OF TECHNOLOGY

## Slide 7: Activity Precedence Table
ID | Activity | Predecessor
A | Requirement Analysis | —
B | Literature Survey | A
C | System Design | B
D | Frontend & Backend Development | C
E | AI & IoT Integration | D
F | System Integration | E
G | Testing & Optimization | F
H | Documentation & Presentation | G
KNOWLEDGE INSTITUTE OF TECHNOLOGY

## Slide 8: Glossary:
KNOWLEDGE INSTITUTE OF TECHNOLOGY
AI: Artificial Intelligence used for health-data analysis.
IoT: Internet of Things for connecting healthcare sensors.
BLE: Bluetooth Low Energy for wearable communication.
MQTT: Lightweight communication protocol for IoT data.
SpO₂: Peripheral oxygen saturation.
PPG: Photoplethysmography used for heart-rate and SpO₂ sensing.
FCM: Firebase Cloud Messaging for push notifications.
Anomaly: Vital reading outside the patient's configured normal range.
Fall Event: Free-fall followed by impact and post-impact stillness.
Caregiver Dashboard: Interface for family members/caregivers.
Doctor Dashboard: Interface for healthcare professionals.

## Slide 9: Core Technologies & Principles
KNOWLEDGE INSTITUTE OF TECHNOLOGY
ARTIFICIAL INTELLIGENCE
Analyses vital signs.
Detects abnormal readings and fall events.
IoT & WEARABLE SENSORS
Measures heart rate, SpO₂, temperature and motion.
CLOUD COMPUTING
Stores and synchronises patient health information.
WEB TECHNOLOGY
React provides dashboards.
Node.js and Express provide backend services.
AUTHENTICATION
Firebase Authentication supports patient, caregiver and doctor roles.
NOTIFICATION
FCM push notifications and SMS provide emergency alerts.

## Slide 10: Concept Rules & Laws
KNOWLEDGE INSTITUTE OF TECHNOLOGY
VITAL MONITORING PRINCIPLE Wearable sensors continuously collect physiological and motion data.
ANOMALY DETECTION PRINCIPLE New readings are compared with personalised normal threshold ranges.
FALL DETECTION PRINCIPLE A fall is identified through the sequence:
FREE FALL → IMPACT → POST-IMPACT STILLNESS
ALERT PRINCIPLE Detected anomalies or falls generate alerts for linked caregivers and doctors.
TREND ANALYSIS PRINCIPLE Historical readings are aggregated to identify gradual changes in patient condition. .

## Slide 11: System Components & Technologies
KNOWLEDGE INSTITUTE OF TECHNOLOGY
Technology / Component | Purpose
PPG Sensor | Heart Rate & SpO₂ Monitoring
Temperature Sensor | Body Temperature Monitoring
Accelerometer / Gyroscope | Motion & Fall Detection
ESP32 | Sensor Processing & Control
BLE / Wi-Fi | Wireless Data Transmission
MQTT | Real-Time Data Communication
Firebase / Node.js / Express | Cloud & Backend Processing
React.js / FCM / SMS | Dashboard & Emergency Alerts

## Slide 12
KNOWLEDGE INSTITUTE OF TECHNOLOGY
System Model
WEARABLE SENSORS ↓ ESP32 / IoT GATEWAY ↓ BLE / WI-FI / MQTT ↓ CLOUD PLATFORM / FIREBASE ↓ AI HEALTH ANALYSIS ↓ ANOMALY & FALL DETECTION ↓ ALERT & NOTIFICATION SERVICE ↓ CAREGIVER / DOCTOR DASHBOARD

## Slide 13: What-if-Analysis
KNOWLEDGE INSTITUTE OF TECHNOLOGY
Scenario | Expected System Response
Normal Vital Reading | Continue monitoring without alert.
Abnormal Vital Reading | AI flags the abnormal condition
Possible Fall | Analyse fall pattern and generate alert
Critical Vital Condition | Push notification and SMS
Missed Medication | Reminder followed by caregiver escalation
Network Failure | Gateway retries / buffers data
Sensor Disconnection | Device-offline notification

## Slide 14: Conclusion
KNOWLEDGE INSTITUTE OF TECHNOLOGY
The Intelligent Remote Healthcare and Assisted Living Ecosystem demonstrates an integrated remote-monitoring solution combining wearable sensors, IoT communication, cloud computing and AI-based analysis. The system continuously monitors important health and activity parameters, identifies abnormal conditions and possible falls, and provides automated alerts to caregivers and doctors. Medication reminders, historical trend analysis, role-based dashboards and PDF reporting further support continuous patient care. Functional and integration testing showed that the major modules worked as designed, providing a strong prototype foundation for future enhancements such as machine-learning-based detection, additional sensors, GPS tracking, mobile applications, predictive analytics and clinical validation.